## Gantt
SAMPLE MISSION CONTROL WORKPLAN | [13 empty] | To Personalize:
|  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Change the months to actual month names
| W=Workshop, M=Meeting | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | Change these dates to the Monday dates
Prepare for success (Chapter 1)
| Identify & interview stakeholders | [12 empty] | Add in any extra details, or change the shading | bar: Month 1 1 to Month 1 2
| Determine working team & agree workplan | [12 empty] | to extend the time span required | bar: Month 1 3 to Month 1 4
Get the Facts (Chapter 2)
| Gather insights on your organization, clients, sector & environment | [12 empty] | Move M (meeting dates) or W (workshop) dates | bar: Month 2 1 to Month 2 4
| Set your goal (Chapter 3) | [12 empty] | as appropriate | bar: Month 2 4
Identify your options (Chapter 4)
Develop first 'tree' with broadest range of ideas | bar: Month 2 4
Test and refine tree with selected stakeholders | bar: Month 3 1
Identify what works (Chapter 5)
Expert interviews
Conduct research
Estimate relative imapct
Know Yourselves (Chapter 6)
Review data on your physical and financial assets | bar: Month 3 4
Discuss and agree organizational strengths | bar: Month 3 4
Choose (Chapter 7) | bar: Month 3 4
Tell your story (Chapter 8) | bar: Month 3 4
Action plan (Chapter 9) | bar: Month 3 4
Share updates with stakeholders | bar: Month 1 1; Month 3 1; Month 3 4